## ControlTowerIntake
Project ID | Project Name | Single-Threaded Owner (VP+) | Initiative Owner (VP+) | Problem Statement | Desired Business Outcome | Success KPIs | Estimated Revenue Impact | Estimated Efficiency Impact | Gross Benefit | Net Benefit | Redeployment Location | Metric Improvement | SLA Driver? | SLA Driver Description | Compliance Driver? | Compliance Driver Description | Reuse Potential? | Reuse Potential Scope | Timeline Period | Approval and Prioritization Target | Design Completion Target | Pilot Rollout Target | Scale Up Target | Dependency 1 | Dependency 2 | Risk | Mitigation
AUTO | Clinical Denial Automation | Jane Doe | John Smith | High denial rate for clinical edits causing rework | Reduce denials and improve first-pass yield | Current 72 percent FPY to 90 percent FPY target | $1.2M annual impact based on 3 percent denial reduction | 4 FTEs saved, $220K cost reduction | 1200000 | 220000 | Reassigned to Patient Access | FPY improvement from 72 percent to 90 percent | Yes |  | No |  | Yes | Across 5 clients | Q3 2025 |  |  |  | Epic integration required | Payer rule library | Automation failure risk | Fallback workflow defined

## LGateRequirements
Project ID | L-Gate | Requirement Name | Requirement Description | Requirement Type | Completion Status | Attachment
| L-Gate 0 Ideation | Intake form completed |  | Document | Not Started
| L-Gate 1 Review and Approval | Base design agreement |  | Document | Not Started
| L-Gate 1 Review and Approval | T-shirt size cost estimate |  | Document | Not Started
| L-Gate 1 Review and Approval | Steerco approval with reason |  | Document | Not Started
| L-Gate 2 Resource Scheduling | Team assignment and RACI |  | Document | Not Started
| L-Gate 2 Resource Scheduling | Specific team members assigned |  | Document | Not Started
| L-Gate 2 Resource Scheduling | Major milestones defined |  | Document | Not Started
| L-Gate 3 Design | Basic requirements document |  | Document | Not Started
| L-Gate 3 Design | AI evaluation and governance form |  | Document | Not Started
| L-Gate 3 Design | KPI movement plan |  | Document | Not Started
| L-Gate 3 Design | Revised scope |  | Document | Not Started
| L-Gate 3 Design | Success criteria |  | Document | Not Started
| L-Gate 3 Design | Revised cost and benefit estimates |  | Document | Not Started
| L-Gate 4 Build and Release | UAT plan and results |  | Document | Not Started
| L-Gate 4 Build and Release | Change management and roll out plan |  | Document | Not Started
| L-Gate 4 Build and Release | Pilot goals and results |  | Document | Not Started
| L-Gate 4 Build and Release | Revised cost and benefits |  | Document | Not Started
| L-Gate 5 Full Scale Roll-Out | Updated milestones |  | Document | Not Started
| L-Gate 5 Full Scale Roll-Out | Ongoing KPI monitoring |  | Document | Not Started
| L-Gate 5 Full Scale Roll-Out | Financial impact |  | Document | Not Started
| L-Gate 6 Value Realization | Ongoing KPI monitoring |  | Document | Not Started
| L-Gate 6 Value Realization | Financial impact |  | Document | Not Started

## ProjectGateDetails
Project ID | L-Gate | Artifact Name | Notes | Status | Owner | Due Date | Attachment
AUTO | L-Gate 1 Review and Approval | Base design agreement |  | In Progress | Jane Doe

## ControlTowerActions
Project ID | Action Date | Gate at Time of Action | Action Type | Decision | Notes | Entered By
AUTO | 2025-01-12 | L-Gate 1 Review and Approval | Prioritization | Approved | Approved to advance to gate 2 | Jane Doe

## LGate0Ideation
Requirement Name | Requirement Description | Requirement Type
Intake form completed |  | Document

## LGate1ReviewandApproval
Requirement Name | Requirement Description | Requirement Type
Base design agreement |  | Document
T-shirt size cost estimate |  | Document
Steerco approval with reason |  | Document

## LGate2ResourceScheduling
Requirement Name | Requirement Description | Requirement Type
Team assignment and RACI |  | Document
Specific team members assigned |  | Document
Major milestones defined |  | Document

## LGate3Design
Requirement Name | Requirement Description | Requirement Type
Basic requirements document |  | Document
AI evaluation and governance form |  | Document
KPI movement plan |  | Document
Revised scope |  | Document
Success criteria |  | Document
Revised cost and benefit estimates |  | Document

## LGate4BuildandRelease
Requirement Name | Requirement Description | Requirement Type
UAT plan and results |  | Document
Change management and roll out plan |  | Document
Pilot goals and results |  | Document
Revised cost and benefits |  | Document

## LGate5FullScaleRollOut
Requirement Name | Requirement Description | Requirement Type
Updated milestones |  | Document
Ongoing KPI monitoring |  | Document
Financial impact |  | Document

## LGate6ValueRealization
Requirement Name | Requirement Description | Requirement Type
Ongoing KPI monitoring |  | Document
Financial impact |  | Document