## Report (2)
Initiative name | Capability Name | Capability reference # | Pod | Value Stream | Funding Lane | Size | Capability status Aha | Capability LGate | Now/Next/Later Calculated | Capability start date | Capability end date | Initiative LGate
Appeal Process Automation | Automated appeal for ED downgrade | BACKRCM-E-768 | Technical Appeal Automation | Revenue Protection + Payer | Strategic | Large | Shipped | L6 | Now | 2024-07-29 | 2025-11-30 | L4
Appeal Process Automation | Automated submission of RFI data | BACKRCM-E-793 | Technical Appeal Automation | Revenue Protection + Payer | Strategic | Large | Shipped | L6 | Need Timeframe |  |  | L4
Appeal Process Automation | Automated appeal low balance clinical denials | BACKRCM-E-797 | Technical Appeal Automation | Revenue Protection + Payer | Strategic | Medium | Validating | L4 | Now | 2025-07-31 | 2026-02-25 | L4
Appeal Process Automation | EOB submission to secondary payer | BACKRCM-E-780 | Technical Appeal Automation | Revenue Protection + Payer | Strategic | Medium | Building | L4 | Now | 2025-10-08 | 2025-12-17 | L4
Appeal Process Automation | Recover unsubmitted ED downgrades revenue | BACKRCM-E-782 | Technical Appeal Automation | Revenue Protection + Payer | Strategic | Medium | Building | L4 | Next | 2026-02-26 | 2026-05-06 | L4
Appeal Process Automation | RFI/ ED Downgrade analytics | BACKRCM-E-734 | Technical Appeal Automation | Revenue Protection + Payer | Strategic | Medium | Shipped | L6 | Now | 2025-05-22 | 2025-10-08 | L4
Appeal Process Automation | Auto Adjust Balance if no Additional Payment After Appeal | BACKRCM-E-861 | Technical Appeal Automation | Revenue Protection + Payer | Strategic | Medium | Defining | L2 | Later | 2026-07-01 | 2026-09-30 | L2
Appeal Process Automation | Auto-Adjust Remaining Balance on Accounts with Appeals Filed | BACKRCM-E-862 | Technical Appeal Automation | Revenue Protection + Payer | Strategic | Medium | Defining | L2 | Later | 2026-10-01 | 2026-12-31 | L2
Appeal Process Automation | Auto-Documentation Create Rules for Document Requests Only | BACKRCM-E-868 | Technical Appeal Automation | Revenue Protection + Payer | Strategic | Medium | Defining | L2 | Later | 2028-07-01 | 2028-09-30 | L2
Appeal Process Automation | Automate Bad Debt Account Reconciliation | BACKRCM-E-867 | Technical Appeal Automation | Revenue Protection + Payer | Strategic | Medium | Defining | L2 | Later | 2028-01-01 | 2028-06-30 | L2
Appeal Process Automation | Automated Underpayment Appeal Creation and Submission | BACKRCM-E-864 | Technical Appeal Automation | Revenue Protection + Payer | Strategic | Medium | Defining | L2 | Later | 2027-04-01 | 2027-09-30 | L2
Appeal Process Automation | Automate Insights for Self-Pay Account Management | BACKRCM-E-866 | Technical Appeal Automation | Revenue Protection + Payer | Strategic | Medium | Defining | L2 | Later | 2027-10-01 | 2027-12-31 | L2
Appeal Process Automation | Automate the Identification and Closure of Appeals with No Payment for Over 90 Days | BACKRCM-E-863 | Technical Appeal Automation | Revenue Protection + Payer | Strategic | Medium | New | L1 | Later | 2026-10-01 | 2026-12-31 | L2
Appeal Process Automation | Automatically Identify & Update Denial Adjustments at Gross Charges for Epic Clients | BACKRCM-E-860 | Technical Appeal Automation | Revenue Protection + Payer | Strategic | Medium | Defining | L2 | Later | 2026-07-01 | 2026-09-30 | L2
Appeal Process Automation | Automatically Submit Medical Records Received from Epic ADR to Payers | BACKRCM-E-855 | Technical Appeal Automation | Revenue Protection + Payer | Strategic | Medium | New | L1 | Now | 2025-12-18 | 2026-03-31 | L2
Appeal Process Automation | Auto Update Appeal Status for Availity Payors | BACKRCM-E-865 | Technical Appeal Automation | Revenue Protection + Payer | Strategic | Medium | Defining | L2 | Later | 2027-01-01 | 2027-03-01 | L2
Appeal Process Automation | Replace Datavant Action Log with New API and Update Reporting | BACKRCM-E-859 | Technical Appeal Automation | Revenue Protection + Payer | Strategic | Large | Defining | L2 | Now | 2025-12-18 | 2026-06-30 | L2
Appeal Process Automation | Self-Service Configuration for Operations | BACKRCM-E-792 | Technical Appeal Automation | Revenue Protection + Payer | Strategic | Medium | Will not implement |  | Kill | 2027-01-01 | 2027-03-31 | L2
Appeal Process Automation | xAPA - Incorporate Operational Feedback and Enhancement Requests into Existing Process | BACKRCM-E-800 | Technical Appeal Automation | Revenue Protection + Payer | Strategic |  | Building | L4 | Now | 2025-05-22 | 2026-07-15 | L2
AR Agent | Adjustment Integration in Non Epic Host for AR Follow Up Agent | RPA-E-53 | Data Integration | Revenue Protection + Payer | Strategic |  | New | L1 | Now | 2025-05-01 | 2025-12-31 | L4
AR Agent | Multi-Payer Expansion & Optimization | INTER-E-253 | Data Integration | Revenue Protection + Payer | Strategic |  | New | L1 | Later | 2026-07-01 | 2026-09-30 | L4
AR Agent | MVP | INTER-E-252 | Data Integration | Revenue Protection + Payer | Strategic |  | New | L1 | Next | 2026-05-01 | 2026-06-30 | L4
AR Agent | Multi-Payer Expansion & Optimization | INTER-E-249 | Data Integration | Revenue Protection + Payer | Strategic |  | New | L1 | Next | 2026-05-01 | 2026-07-31 | L4
AR Agent | MVP | INTER-E-233 | Data Integration | Revenue Protection + Payer | Strategic |  | New | L1 | Next | 2026-02-26 | 2026-04-30 | L4
AR Agent | AR Agent ¦ Acute - Automate Appeal Follow-Up Status and Slow Response Escalation | BACKRCM-E-1008 | AR Agent | Revenue Protection + Payer | Strategic |  | New | L1 | Next | 2026-04-01 | 2026-06-30 | L4
AR Agent | AR Agent ¦ Acute - Automate Resolution of Eligibility/COB Denials | BACKRCM-E-1003 | AR Agent | Revenue Protection + Payer | Strategic | X-Large | Building | L4 | Now | 2025-12-18 | 2026-03-31 | L4
AR Agent | AR Agent ¦ Acute - Touchless Resolution of Denied Accounts | BACKRCM-E-828 | AR Agent | Revenue Protection + Payer | Strategic | X-Large | New | L1 | Next | 2026-01-01 | 2026-12-31 | L4
AR Agent | AR Agent ¦ Acute - Touchless Resolution of Insurance Aged, No Response Accounts | BACKRCM-E-827 | AR Agent | Revenue Protection + Payer | Strategic | X-Large | Building | L4 | Now | 2025-12-18 | 2026-06-30 | L4
AR Agent | AR Agent ¦ Acute - Touchless Resolution of Insurance Paid, No Denial Accounts | BACKRCM-E-824 | AR Agent | Revenue Protection + Payer | Strategic | X-Large | Building | L4 | Now | 2025-10-01 | 2026-02-11 | L4
AR Agent | Payor Agent Hold with Infinitus | BACKRCM-E-833 | Virtual Agent | Revenue Protection + Payer | Strategic |  | Building | L4 | Next | 2026-01-15 | 2026-04-30 | L4
AR Agent | AR Agent ¦ PRC - Touchless Resolution of Denied Accounts | BACKRCM-E-829 | AR Agent | Revenue Protection + Payer | Strategic | X-Large | New | L1 | Next | 2026-03-02 | 2026-12-31 | L4
AR Agent | AR Agent ¦ PRC - Touchless Resolution of Insurance Aged, No Response Accounts | BACKRCM-E-826 | AR Agent | Revenue Protection + Payer | Strategic | X-Large | New | L1 | Later | 2026-06-01 | 2026-12-31 | L4
AR Agent | AR Agent ¦ PRC - Touchless Resolution of Insurance Paid, No Denial Accounts | BACKRCM-E-825 | AR Agent | Revenue Protection + Payer | Strategic | X-Large | Building | L4 | Next | 2026-03-02 | 2026-12-31 | L4
AR Agent | Multi-Payer Expansion & Optimization | INTER-E-255 | Data Integration | Revenue Protection + Payer | Strategic |  | New | L1 | Later | 2026-07-01 | 2026-09-30 | L4
AR Agent | MVP | INTER-E-254 | Data Integration | Revenue Protection + Payer | Strategic |  | New | L1 | Next | 2026-05-01 | 2026-06-30 | L4
AR Agent | Multi-Payer Expansion & Optimization | INTER-E-225 | Data Integration | Revenue Protection + Payer | Strategic |  | Building | L4 | Now | 2025-10-09 | 2026-04-30 | L4
AR Agent | MVP (Anthem via Availity for VCU & Carillion) | INTER-E-224 | Data Integration | Revenue Protection + Payer | Strategic |  | Shipped | L6 | Now | 2025-07-31 | 2025-12-17 | L4
AR Agent | Eligibility API Multi-Payer & Client Expansion | INTER-E-215 | Data Integration | Revenue Protection + Payer | Strategic |  | Ready |  | Now | 2025-12-18 | 2026-04-30 | L4
AR Agent | Eligibility API MVP (Initial Payer & Client Rollout) | INTER-E-213 | Data Integration | Revenue Protection + Payer | Strategic |  | Building | L4 | Now | 2025-10-09 | 2026-02-25 | L4
AR Agent | Multi-Payer Expansion & Optimization | INTER-E-257 | Data Integration | Revenue Protection + Payer | Strategic |  | New | L1 | Later | 2026-09-01 | 2026-11-30 | L4
AR Agent | MVP | INTER-E-256 | Data Integration | Revenue Protection + Payer | Strategic |  | New | L1 | Later | 2026-07-01 | 2026-08-31 | L4
AR Agent | Move Balance Integration in Non Epic Host for AR Follow Up Agent | RPA-E-54 | Data Integration | Revenue Protection + Payer | Strategic |  | Building | L4 | Now | 2025-07-17 | 2025-09-01 | L4
AR Agent | Notes Integration in Non Epic Host for AR Follow Up Agent | RPA-E-55 | Data Integration | Revenue Protection + Payer | Strategic |  | Shipped | L6 | Now | 2025-05-01 | 2025-12-31 | L4
AR Agent | Payor Integration for AR Follow UP Agent | RPA-E-60 | Data Integration | Revenue Protection + Payer | Strategic |  | Building | L4 | Now | 2025-08-28 | 2025-08-28 | L4
AR Agent | Rebill Integration in Non Epic Host for AR Follow Up Agent | RPA-E-56 | Data Integration | Revenue Protection + Payer | Strategic |  | Building | L4 | Now | 2025-05-01 | 2025-12-31 | L4
AR Agent | Multi-Payer Expansion & Optimization | INTER-E-251 | Data Integration | Revenue Protection + Payer | Strategic |  | New | L1 | Next | 2026-05-01 | 2026-07-31 | L4
AR Agent | MVP | INTER-E-250 | Data Integration | Revenue Protection + Payer | Strategic |  | New | L1 | Next | 2026-02-26 | 2026-04-30 | L4
AR Agent | Multi-Payer Expansion & Optimization | INTER-E-234 | Data Integration | Revenue Protection + Payer | Strategic |  | New | L1 | Now | 2025-12-18 | 2026-04-30 | L4
AR Agent | MVP (Anthem via Availity for VCU & Carillion) | INTER-E-232 | Data Integration | Revenue Protection + Payer | Strategic |  | Building | L4 | Now | 2025-10-09 | 2026-02-25 | L4
AR Agent | Update Coverage Change in Non Epic Host for AR Follow Up Agent | RPA-E-57 | Data Integration | Revenue Protection + Payer | Strategic |  | Building | L4 | Now | 2025-05-01 | 2025-12-31 | L4
AR Agent | Update Guarantor in Non Epic Host for AR Follow Up Agent | RPA-E-59 | Data Integration | Revenue Protection + Payer | Strategic |  | Building | L4 | Now | 2025-05-01 | 2025-12-31 | L4
AR Agent | Update Patient Demographics in Non Epic Host for AR Follow Up Agent | RPA-E-58 | Data Integration | Revenue Protection + Payer | Strategic |  | Building | L4 | Now | 2025-05-01 | 2025-12-31 | L4
Authorization Enhancements | #REF! | FRONTRCM-E-197 | EIQ Clear | Financial Clearance + Prediction | Strategic | X-Small | Designing | L3 | Later | 2026-10-21 | 2026-11-18 | L3
Authorization Enhancements | All Payer Medical Necessity | EIQCLEAR-E-68 | EIQ Clear | Financial Clearance + Prediction | Strategic | Large | Will not implement |  | Kill | 2025-07-01 | 2026-03-13 | L3
Authorization Enhancements | Automate Post back to Epic via AutoStart Rules | FRONTRCM-E-125 | EIQ Clear | Financial Clearance + Prediction | Strategic | X-Small | Ready |  | Now | 2025-12-18 | 2026-02-11 | L3
Authorization Enhancements | CPT Mismatch/Amended Authorization Exception Worklist | FRONTRCM-E-140 | EIQ Clear | Financial Clearance + Prediction | Strategic |  | Will not implement |  | Kill | 2026-10-01 | 2027-06-30 | L3
Authorization Enhancements | EIQ Clear - VUR Authorizations | FRONTRCM-E-146 | EIQ Clear | Financial Clearance + Prediction | Strategic |  | Defining | L2 | Later | 2027-04-01 | 2027-12-30 | L3
Authorization Enhancements | eMPA Compatibility | FRONTRCM-E-142 | EIQ Clear | Financial Clearance + Prediction | Strategic | Small | Building | L4 | Now | 2025-12-18 | 2026-02-11 | L3
Authorization Enhancements | EPIC Insurance Updates Automation | EIQCLEAR-E-64 | EIQ Clear | Financial Clearance + Prediction | Strategic |  | Defining | L2 | Now | 2023-01-02 | 2023-03-31 | L3
Authorization Enhancements | Infusion - Biosimilar Drugs by Payers | FRONTRCM-E-143 | EIQ Clear | Financial Clearance + Prediction | Strategic | Medium | Defining | L2 | Later | 2027-10-01 | 2028-06-29 | L3
Authorization Enhancements | Missing Account Number- Auto create Action Log & send to RPA | FRONTRCM-E-200 | EIQ Clear | Financial Clearance + Prediction | Strategic | Large | Designing | L3 | Now | 2025-12-18 | 2026-02-25 | L3
Authorization Enhancements | Referral Linking Enhancements - Link by MRN | FRONTRCM-E-212 | EIQ Clear | Financial Clearance + Prediction | Strategic | Small | Defining | L2 | Now | 2025-12-18 | 2026-02-25 | L3
Authorization Enhancements | Tracking Disposition Reasons for ReAssignments _ Pre-Auth Tasks and Action Logs | FRONTRCM-E-174 | EIQ Clear | Financial Clearance + Prediction | Strategic | X-Small | Designing | L3 | Next | 2026-02-26 | 2026-07-01 | L3
Authorization Enhancements | Waystar DeepLink Integration | FRONTRCM-E-141 | EIQ Clear | Financial Clearance + Prediction | Strategic | Small | Defining | L2 | Next | 2026-04-01 | 2026-09-30 | L3
Autonomous Coding | 360 Encompass/Cloud/HB CAC | AC-E-20 | Autonomous Coding | Clinical | Strategic | X-Large | Building | L4 | Now | 2025-06-01 | 2026-04-01 | L4
Autonomous Coding | 360 Encompass Foundational | AC-E-19 | Autonomous Coding | Clinical | Strategic | X-Large | Building | L4 | Now | 2025-06-01 | 2026-04-01 | L4
Autonomous Coding | HB Autonomous Inpatient | AC-E-15 | Autonomous Coding | Clinical | Strategic | XX-Large | Designing | L3 | Later | 2027-01-01 | 2027-07-30 | L4
Autonomous Coding | HB Autonomous Outpatient | AC-E-14 | Autonomous Coding | Clinical | Strategic | X-Large | Building | L4 | Now | 2025-06-01 | 2026-06-05 | L4
Autonomous Coding | PB Autonomous | AC-E-17 | Autonomous Coding | Clinical | Strategic | X-Large | Building | L4 | Now | 2025-06-01 | 2026-06-19 | L4
Autonomous Coding | PB CAC | AC-E-18 | Autonomous Coding | Clinical | Strategic | X-Large | Building | L4 | Now | 2025-06-01 | 2026-06-19 | L4
Cash Posting Agent | Virtual credit card workflow automation | BACKRCM-E-877 | Cash Automation | Revenue Protection + Payer | Strategic | Medium | New | L1 | Later | 2029-04-01 | 2029-09-30
Cash Posting Agent | Cash Posting - Automate Cash Posting Processing Errors | BACKRCM-E-869 | Cash Automation | Revenue Protection + Payer | Strategic |  | Will not implement |  | Kill | 2025-12-01 | 2026-09-30 | L4
Cash Posting Agent | Cash Posting - Automated Retrieval of Missing Remit | BACKRCM-E-760 | Cash Automation | Revenue Protection + Payer | Strategic |  | Building | L4 | Now | 2025-06-01 | 2025-10-31 | L4
Cash Posting Agent | Cash posting error reason and recommendation | BACKRCM-E-776 | Cash Automation | Revenue Protection + Payer | Strategic |  | Building | L4 | Now | 2025-05-22 | 2026-02-25 | L4
Cash Posting Agent | Cash Posting - Error Resolution Recommendation Phase 2 Errors | BACKRCM-E-846 | Cash Automation | Revenue Protection + Payer | Strategic |  | Defining | L2 | Next | 2026-05-01 | 2026-06-29 | L4
Cash Posting Agent | Identify and correct remittance errors using charge file | BACKRCM-E-870 | Cash Automation | Revenue Protection + Payer | Strategic |  | New | L1 | Next | 2026-01-01 | 2026-10-01 | L4
Cash Reconciliation | Auto match credit card payments | PDB-E-37 | Cash Automation | Revenue Protection + Payer | Strategic | Medium | Defining | L2 | Later | 2026-07-01 | 2026-12-31 | L4
Cash Reconciliation | Automatch Functionality Standardization | BACKRCM-E-1005 | Cash Automation | Revenue Protection + Payer | Strategic | Small | Building | L4 | Now | 2025-12-18 | 2026-02-25 | L4
Cash Reconciliation | Automation for daily cash reconciliation | PDB-E-41 | Cash Automation | Revenue Protection + Payer | Strategic |  | Building | L4 | Now | 2024-12-16 | 2025-05-27 | L4
Cash Reconciliation | Cash Recon Zero Pay reconciliation | BACKRCM-E-875 | Cash Automation | Revenue Protection + Payer | Strategic | Medium | New | L1 | Later | 2028-10-01 | 2029-03-31 | L4
Cash Reconciliation | Clearing account and non-patient cash reporting | BACKRCM-E-588 | Cash Automation | Revenue Protection + Payer | Strategic |  | Shipped | L6 | Now | 2025-03-31 | 2025-10-31 | L4
Cash Reconciliation | Offsetting transaction resolution | BACKRCM-E-808 | Cash Automation | Revenue Protection + Payer | Strategic |  | Shipped | L6 | Now | 2025-09-01 | 2025-10-30 | L4
Cash Reconciliation | Cash Recon - Performance Enhancements | BACKRCM-E-766 | Cash Automation | Revenue Protection + Payer | Strategic |  | Building | L4 | Now | 2025-05-22 | 2025-12-31 | L4
Cash Reconciliation | Improve PLB workflow and automation | BACKRCM-E-871 | Cash Automation | Revenue Protection + Payer | Strategic |  | New | L1 | Later | 2026-10-01 | 2027-03-31 | L2
Cedar | Improve patient engagement and patient financial yield | INTER-E-244 | Data Integration | Patient Engagement | Strategic | Large | New | L1 | Later | 2026-07-06 | 2027-03-31
Clinical Integration | Combining concurrent CDI + concurrent UR logic to create one workflow and one team | MIDRCM-E-206 | EIQ Integrity | Revenue Protection + Payer | Strategic | Small | New | L1 | Later | 2031-01-01 | 2031-03-31
Clinical Integration | Logic arbitration for LLM vs. ML vs. hard codes for insights and queries | MIDRCM-E-205 | EIQ Integrity | Revenue Protection + Payer | Strategic | Small | New | L1 | Later | 2030-10-01 | 2030-12-31
Clinical Integration | Query builder to integrate natively into client EMR | MIDRCM-E-207 | EIQ Integrity | Revenue Protection + Payer | Strategic | Small | New | L1 | Later | 2031-04-01 | 2031-06-30
Clinical Reasoning | Coding denial reasoning | BACKRCM-E-856 | Clinical Appeals | Clinical | Strategic | Large | New | L1 | Next | 2026-03-01 | 2026-10-01
Clinical Reasoning | Coding review model for DRG and CC/MCC | MIDRCM-E-204 | EIQ Integrity | Clinical | Strategic | Small | New | L1 | Later | 2030-07-01 | 2030-09-30
Clinical Reasoning | Concurrent CDI logic to replace Solventum CDI logic | MIDRCM-E-202 | EIQ Integrity | Clinical | Strategic | Small | New | L1 | Later | 2030-01-01 | 2030-03-31
Clinical Reasoning | Elixhauser flagging | MIDRCM-E-203 | EIQ Integrity | Clinical | Strategic | Small | New | L1 | Later | 2030-04-01 | 2030-06-30
Clinical Reasoning | Post discharge CDI logic to replace Solventum CDI logic | MIDRCM-E-201 | EIQ Integrity | Clinical | Strategic | Small | New | L1 | Later | 2029-10-01 | 2029-12-31
Clinical Reasoning | Reasoning model for charge capture away from hard rules | MIDRCM-E-200 | EIQ Integrity | Clinical | Strategic | Small | New | L1 | Later | 2029-07-01 | 2029-09-30
Clinical Reasoning | Live transcription and translation of encounters into clinical docs and codes | BACKRCM-E-879 | Clinical Appeals | Clinical | Strategic | Small | New | L1 | Later | 2030-10-01 | 2030-12-31
Credit Automation - Phase 2 | Acute credit overpayment letter notification | BACKRCM-E-647 | EIQ Collect | Platform | Platform |  | Shipped | L6 | Now | 2025-06-01 | 2025-10-10 | L4
Credit Automation - Phase 2 | Credits Automation Configuration Manager | BACKRCM-E-1002 | EIQ Collect | Platform | Platform |  | New | L1 | Later | 2026-09-01 | 2027-01-01 | L4
Credit Automation - Phase 2 | Credit Automation - V 1.0 - Generate the data files (CSV and PDF) and send to Vendor (RevSpring) - PB (PRC) | INTER-E-148 | Data Integration | Revenue Protection + Payer | Platform |  | Ready |  | Now | 2025-01-01 | 2027-02-01 | L4
Credit Automation - Phase 2 | Automated credit Adjustment to Income | BACKRCM-E-998 | EIQ Collect | Revenue Protection + Payer | Core |  | New | L1 | Later | 2028-04-01 | 2028-07-01 | L4
Credit Automation - Phase 2 | Automated Credit Overpayment Letters | BACKRCM-E-683 | EIQ Collect | Revenue Protection + Payer | Core |  | Defining | L2 | Later | 2028-07-01 | 2028-10-01 | L4
Data acquisition | Master Specs (Data Mastering) - Q4 2025 Spec Release and Spec Rollout | DATA-E-392 | Data Platform | Platform | Platform |  | Validating | L4 | Now | 2025-05-22 | 2025-12-17 | L4
Data acquisition | Work Queue Data Acquisition | MDM-E-58 | Data Platform | Platform | Platform |  | Shipped | L6 | Now | 2025-02-03 | 2025-12-31 | L4
Data acquisition | Coding - Comparative coding | DATA-E-408 | Data Platform | Platform | Platform |  | Building | L4 | Now | 2025-07-31 | 2026-03-31 | L4
Data Integration | Artiva/Finvi Integration POC | RPA-E-51 | Data Integration | Platform | Platform |  | Shipped | L6 | Now | 2025-10-01 | 2025-12-31 | L3
Data Integration | Artiva/Finvi Integration - Production | RPA-E-52 | Data Integration | Platform | Platform | Medium | New | L1 | Next | 2026-03-01 | 2026-12-31 | L3
EIQ Clear | EIQ Clear Cerner Integration pilot with Nicklaus | EIQCLEAR-E-65 | EIQ Clear | Financial Clearance + Prediction | Strategic | Small | Building | L4 | Now | 2025-11-03 | 2026-03-31 | L4
EIQ Clear | EIQ Clear Meditech Integration | EIQCLEAR-E-75 | EIQ Clear | Financial Clearance + Prediction | Strategic | Medium | Defining | L2 | Next | 2026-02-26 | 2026-07-01 | L4
EIQ Clear | Nicklaus Cerner/Nordic Implementation | INTER-E-243 | Data Integration | Financial Clearance + Prediction | Strategic |  | Building | L4 | Now | 2025-10-09 | 2026-02-25 | L4
EIQ Collect | PRC - Claim Status Vendor Reduction | BACKRCM-E-649 | EIQ Collect | Revenue Protection + Payer | Core |  | Shipped | L6 | Now | 2025-05-15 | 2025-10-19 | L4
EIQ Collect | Authorization Service Line Expansion | FRONTRCM-E-139 | EIQ Clear | Financial Clearance + Prediction | Strategic | Large | Defining | L2 | Later | 2026-05-26 | 2027-03-24 | L3
EIQ Collect | Audit Process Automation IR Hand Off to Owning Team Thru Submission | BACKRCM-E-1013 | EIQ Collect | Revenue Protection + Payer | Strategic | Medium | New | L1 | Later | 2029-10-01 | 2030-04-01
EIQ Collect | Correspondence through SSI | BACKRCM-E-1010 | EIQ Collect | Revenue Protection + Payer | Strategic |  | New | L1 | Now | 2000-01-01 | 2000-01-01
EIQ Collect | Insurance Verification for Accident Claims | BACKRCM-E-1012 | EIQ Collect | Revenue Protection + Payer | Strategic |  | New | L1 | Later | 2028-10-01 | 2029-04-01
EIQ Collect | Appeal Automation into PRC | BACKRCM-E-1014 | EIQ Collect | Revenue Protection + Payer | Strategic |  | New | L1 | Later | 2030-04-01 | 2030-10-01
EIQ Collect | EIQ Collect | BACKRCM-E-1015 | EIQ Collect | Revenue Protection + Payer | Core |  | New | L1 | Later | 2030-04-01 | 2031-04-01
EIQ Collect | EIQ Collect (PRO) | BACKRCM-E-1016 | EIQ Collect | Revenue Protection + Payer | Core |  | New | L1 | Later | 2031-04-01 | 2032-04-01
EIQ Enforce Modernization | Underpayments/CM rules engine optimization | INSOVER-E-78 | EIQ Enforce | Revenue Protection + Payer | Strategic | Medium | Building | L4 | Now | 2025-01-01 | 2025-12-31 | L4
EIQ Enforce Modernization | AI Contract Loading | INSOVER-E-99 | EIQ Enforce | Revenue Protection + Payer | Core | Medium | New | L1 | Later | 2029-10-01 | 2030-03-31
EIQ Enforce Modernization | Automatically export and load terms and pricing from raw contracts in the contract management module | INSOVER-E-100 | EIQ Enforce | Revenue Protection + Payer | Core | Small | New | L1 | Later | 2030-04-01 | 2030-06-30
EIQ Enforce Modernization | Use a reasoning model to determine the root cause of the variance | INSOVER-E-96 | EIQ Enforce | Revenue Protection + Payer | Core | Small | New | L1 | Later | 2031-01-01 | 2031-03-31
EIQ Enforce Modernization | Use a reasoning model to review variances to determine true or false variances | INSOVER-E-95 | EIQ Enforce | Revenue Protection + Payer | Core | Medium | New | L1 | Later | 2030-07-01 | 2030-12-31
EIQ Enforce Modernization | Use a reasoning model to review zero balance accounts for errors not commonly caught by contract management engines | INSOVER-E-98 | EIQ Enforce | Revenue Protection + Payer | Core | Small | New | L1 | Later | 2031-07-01 | 2031-09-30
EIQ Enforce Modernization | Use the reasoning model to compare payments against contractual and policy terms | INSOVER-E-97 | EIQ Enforce | Revenue Protection + Payer | Core | Small | New | L1 | Later | 2031-04-01 | 2031-06-30
EIQ Enforce Modernization | Auto-generate appeal letters - Underpayments | INSOVER-E-94 | EIQ Enforce | Revenue Protection + Payer | Core | Small | New | L1 | Later | 2032-10-01 | 2032-12-31
EIQ Enforce Modernization | Allow clinical records to be queried for certain data elements - Underpayments | INSOVER-E-93 | EIQ Enforce | Revenue Protection + Payer | Core | Medium | New | L1 | Later | 2032-04-01 | 2032-09-30
EIQ Enforce Modernization | Make available clinical information - Underpayments | INSOVER-E-92 | EIQ Enforce | Revenue Protection + Payer | Core | Medium | New | L1 | Later | 2031-10-01 | 2032-03-31
EIQ Enforce Modernization | Contract management calculations - CAH | INSOVER-E-89 | EIQ Enforce | Revenue Protection + Payer | Core | Small | Will not implement |  | Kill | 2026-01-01 | 2026-03-31
EIQ Enforce Modernization | Contract management calculations - MCRIRF | INSOVER-E-86 | EIQ Enforce | Revenue Protection + Payer | Core | Small | New | L1 | Later | 2027-07-01 | 2027-09-30
EIQ Enforce Modernization | Contract management calculations - MCR SNF | INSOVER-E-88 | EIQ Enforce | Revenue Protection + Payer | Core | Small | New | L1 | Later | 2027-04-01 | 2027-06-30
EIQ Enforce Modernization | Contract management calculations - State MCD APR-DRG IP | INSOVER-E-83 | EIQ Enforce | Revenue Protection + Payer | Core | Medium | New | L1 | Next | 2026-04-01 | 2026-09-30
EIQ Enforce Modernization | Contract management calculations - State MCD EAPG OP | INSOVER-E-84 | EIQ Enforce | Revenue Protection + Payer | Core | Medium | New | L1 | Later | 2027-10-01 | 2028-03-31
EIQ Enforce Modernization | Contract management calculations - Transplants | INSOVER-E-85 | EIQ Enforce | Revenue Protection + Payer | Core | X-Large | New | L1 | Later | 2028-04-01 | 2029-03-31
EIQ Enforce Modernization | Contract management calculations - Tricare IPPS | INSOVER-E-90 | EIQ Enforce | Revenue Protection + Payer | Core | Small | New | L1 | Later | 2026-10-01 | 2026-12-31
EIQ Enforce Modernization | Contract management calculations - Tricare OPPS | INSOVER-E-87 | EIQ Enforce | Revenue Protection + Payer | Core | Small | New | L1 | Later | 2027-01-01 | 2027-03-31
EIQ Enforce Modernization | Contract Management Tool Enhancements | INSOVER-E-75 | EIQ Enforce | Revenue Protection + Payer | Core | Medium | Building | L4 | Next | 2026-01-01 | 2026-06-30 | L3
EIQ Enforce Modernization | PRC Underpayment WF Tool | INSOVER-E-82 | EIQ Enforce | Revenue Protection + Payer | Core | X-Large | New | L1 | Later | 2026-07-01 | 2027-06-30
EIQ Enforce Modernization | Prioritization | INSOVER-E-91 | EIQ Enforce | Revenue Protection + Payer | Core | Medium | New | L1 | Later | 2029-04-01 | 2029-09-30
EIQ Enforce Modernization | 835/837 processing migration to Azure - Assessments | INTER-E-230 | Data Integration | Enterprise Excellence | Platform | Small | Building | L4 | Now | 2025-10-09 | 2026-01-15 | L4
EIQ Enforce Modernization | 835/837 processing migration to Azure - Daily Processing | INTER-E-246 | Data Integration | Enterprise Excellence | Platform | Small | Defining | L2 | Next | 2026-02-01 | 2026-04-30 | L4
EIQ Enterprise Platform | Add remove reorder insurance. Submit Insurance FHIR API for coverage change criteria validation - POC | INTER-E-248 | Data Integration | Enterprise Excellence | Platform | Medium | Validating | L4 | Now | 2025-09-30 | 2025-12-31 | L4
EIQ Enterprise Platform | Cerner/Nordic integration | INTER-E-247 | Data Integration | Enterprise Excellence | Platform | X-Small | New | L1 | Next | 2026-03-01 | 2026-09-01 | L4
EIQ Integrity Modernization | Automate client CDM updates - EPIC | MIDRCM-E-175 | EIQ Integrity | Revenue Protection + Payer | Strategic | Small | Shipped | L6 | Now | 2025-10-09 | 2026-01-31 | L3
EIQ Integrity Modernization | CDI Prioritization Worklist Module for EIQ Integrity | MIDRCM-E-229 | EIQ Integrity | Revenue Protection + Payer | Strategic |  | New | L1 | Need Timeframe
EIQ Integrity Modernization | CDM updates to be pushed from EIQ Integrity to client EMRs | MIDRCM-E-199 | EIQ Integrity | Revenue Protection + Payer | Strategic | Medium | New | L1 | Later | 2029-01-01 | 2029-06-30 | L3
EIQ Integrity Modernization | Create a CDM module as a part of EIQ Integrity that contains synced copies of client CDMs | MIDRCM-E-196 | EIQ Integrity | Revenue Protection + Payer | Strategic | Large | New | L1 | Later | 2026-11-01 | 2027-07-31 | L3
EIQ Integrity Modernization | Modeling the revenue impact from CDM pricing changes | MIDRCM-E-198 | EIQ Integrity | Revenue Protection + Payer | Strategic | Medium | New | L1 | Later | 2028-07-01 | 2028-12-31 | L3
EIQ Integrity Modernization | Workflow for CDM update requests | MIDRCM-E-197 | EIQ Integrity | Revenue Protection + Payer | Strategic | Medium | New | L1 | Later | 2027-08-01 | 2028-06-30 | L3
EIQ Integrity Modernization | CDM Updates - April 2026 [Middle] | MIDRCM-E-221 | EIQ Integrity | Clinical | Strategic |  | New | L1 | Next | 2026-04-01 | 2026-04-30 | L3
EIQ Integrity Modernization | CDM Updates - February 2026 [Middle] | MIDRCM-E-219 | EIQ Integrity | Clinical | Strategic |  | New | L1 | Next | 2026-02-01 | 2026-02-28 | L3
EIQ Integrity Modernization | DDS Reporting | MIDRCM-E-154 | EIQ Integrity | Revenue Protection + Payer | Strategic | Large | Shipped | L6 | Now | 2025-03-24 | 2025-12-31 | L4
EIQ Integrity Modernization | Identify missing CC/MCC using LLM | MIDRCM-E-187 | Frictionless | Revenue Protection + Payer | Innovation | Large | Designing | L3 | Next | 2026-01-01 | 2026-09-30
EIQ Integrity Modernization | Identify missing CC/MCC using LLM (Phase 2) | MIDRCM-E-226 | Frictionless | Revenue Protection + Payer | Innovation | Large | Building | L4 | Next | 2026-01-01 | 2026-09-30
EIQ Integrity Modernization | Integrate with Solventum for DRG-V Point Solution | MIDRCM-E-171 | EIQ Integrity | Revenue Protection + Payer | Platform | Small | Building | L4 | Now | 2025-05-22 | 2026-05-06 | L4
EIQ Integrity Modernization | Lift Calculation Automation: CDI Validation | MIDRCM-E-192 | EIQ Integrity | Revenue Protection + Payer | Platform | Large | New | L1 | Next | 2026-02-01 | 2026-10-31 | L3
EIQ Integrity Modernization | Lift Calculation Automation: Coding Validation (PRC) | MIDRCM-E-194 | EIQ Integrity | Revenue Protection + Payer | Platform | Large | Will not implement |  | Kill | 2026-02-01 | 2026-10-31 | L3
EIQ Integrity Modernization | Outpatient Integrity Functionality - Soft Coded Surgical CPT Code Errors | MIDRCM-E-230 | EIQ Integrity | Revenue Protection + Payer | Strategic |  | New | L1 | Now | 2023-01-01 |  | L3
EIQ Integrity Modernization | Modeling the revenue impact from CDM pricing changes | MIDRCM-E-208 | Frictionless | ValueX | Strategic | Medium | New | L1 | Later | 2027-01-01 | 2027-04-30
EIQ Integrity Modernization | Scenario modeling | MIDRCM-E-209 | Frictionless | Revenue Generation | Strategic | Medium | New | L1 | Later | 2027-05-01 | 2027-08-31
EIQ Enterprise Platform | Enterprise- Standardized Payer Plan | BACKRCM-E-749 | EIQ Collect | Revenue Protection + Payer | Core |  | Shipped | L6 | Now | 2024-06-03 | 2025-07-30 | L4
EIQ Enterprise Platform | Enterprise Work Management - Exploratory Reporting - Insurance AR, Denials (Clinical and Technical) | BACKRCM-E-641 | EIQ Collect | Revenue Protection + Payer | Core | X-Large | Defining | L2 | Later | 2032-03-01 | 2033-03-01 | L3
Enterprise AP Invoice Automation | [AMN/Aquity] [Ardent] Legacy Vendor Audit 2027 | ANALYTICS-E-267 | Invoice Analytics | Enterprise Excellence | Core | Large | New | L1 | Later | 2027-01-05 | 2027-02-27 | L4
Enterprise AP Invoice Automation | [AP Automation] : Enterprise Audit Data Automation & Results Delivery 2025 | ANALYTICS-E-217 | Invoice Analytics | Enterprise Excellence | Core | Large | Shipped | L6 | Now | 2025-02-24 | 2025-12-17 | L4
Enterprise AP Invoice Automation | [AP Automation] Enterprise Vendor Ingestion Hub 2024 | ANALYTICS-E-162 | Invoice Analytics | Enterprise Excellence | Core | Medium | Shipped | L6 | Now | 2025-01-01 | 2025-12-31 | L4
Enterprise AP Invoice Automation | [AP Automation] Expansion of vendors and grouping of vendors | ANALYTICS-E-245 | Invoice Analytics | Enterprise Excellence | Core |  | Building | L4 | Now | 2025-12-18 | 2026-07-22 | L4
Enterprise AP Invoice Automation | [Bad Debt] Enterprise Vendors Audit 2024 | ANALYTICS-E-167 | Invoice Analytics | Enterprise Excellence | Core |  | Shipped | L6 | Now | 2025-01-27 | 2025-03-21 | L4
Enterprise AP Invoice Automation | [Claim Status] Enterprise Vendor Audit 2026 | ANALYTICS-E-139 | Invoice Analytics | Enterprise Excellence | Core | Large | Defining | L2 | Next | 2026-02-26 | 2026-07-16 | L4
Enterprise AP Invoice Automation | [Coverage Discovery] Enterprise Vendor Audit 2025 | ANALYTICS-E-164 | Invoice Analytics | Enterprise Excellence | Core | X-Small | Shipped | L6 | Now | 2025-01-27 | 2025-04-27 | L4
Enterprise AP Invoice Automation | [Enterprise] Connect to upstream Account reconciliation Back RCM | ANALYTICS-E-268 | Invoice Analytics | Enterprise Excellence | Core | Large | New | L1 | Later | 2027-01-06 | 2027-03-25 | L4
Enterprise AP Invoice Automation | [Enterprise] Invoice evaluation at receipt | ANALYTICS-E-270 | Invoice Analytics | Enterprise Excellence | Core | Large | New | L1 | Later | 2027-01-06 | 2028-01-28 | L4
Enterprise AP Invoice Automation | [Global] Enterprise Back RCM Vendors Audit 2025 | ANALYTICS-E-222 | Invoice Analytics | Enterprise Excellence | Core |  | Shipped | L6 | Now | 2025-04-27 | 2025-10-29 | L4
Enterprise AP Invoice Automation | [Global] Enterprise Front RCM Vendors Audit 2025 | ANALYTICS-E-243 | Invoice Analytics | Enterprise Excellence | Core | Medium | Shipped | L6 | Now | 2025-10-09 | 2025-12-18 | L4
Enterprise AP Invoice Automation | [Global] Enterprise Middle RCM Vendors Audit 2025 | ANALYTICS-E-166 | Invoice Analytics | Enterprise Excellence | Core |  | Shipped | L6 | Now | 2024-12-02 | 2025-12-18 | L4
Enterprise AP Invoice Automation | [Global Vendors] Enterprise Back RCM Vendors Audit 2026 Expansion | ANALYTICS-E-261 | Invoice Analytics | Enterprise Excellence | Core |  | Defining | L2 | Later | 2026-07-07 | 2026-11-07 | L4
Enterprise AP Invoice Automation | [Global Vendors] Enterprise Front RCM Vendors Audit 2026 Expansion | ANALYTICS-E-262 | Invoice Analytics | Enterprise Excellence | Core |  | Defining | L2 | Now | 2025-12-18 | 2026-02-26 | L4
Enterprise AP Invoice Automation | [Global Vendors] Enterprise Middle RCM Vendors Audit 2026 Expansion | ANALYTICS-E-260 | Invoice Analytics | Enterprise Excellence | Core |  | Building | L4 | Now | 2025-12-18 | 2026-02-26 | L4
Enterprise AP Invoice Automation | [Insurance Authorization] Enterprise Vendor Audit 2026 | ANALYTICS-E-257 | Invoice Analytics | Enterprise Excellence | Core |  | Defining | L2 | Later | 2026-09-21 | 2026-12-31 | L4
Enterprise AP Invoice Automation | KTLO & BDD | ANALYTICS-E-163 | Invoice Analytics | Enterprise Excellence | Core |  | Shipped | L6 | Now | 2025-01-27 | 2025-12-17 | L4
Enterprise AP Invoice Automation | KTLO & BDD | ANALYTICS-E-259 | Invoice Analytics | Enterprise Excellence | Core |  | Defining | L2 | Now | 2025-12-18 | 2026-12-31 | L4
Enterprise AP Invoice Automation | [Patient Statements & Digital Payments] Enterprise Vendor Audit 2025 | ANALYTICS-E-165 | Invoice Analytics | Enterprise Excellence | Core | X-Small | Shipped | L6 | Now | 2025-01-01 | 2025-03-21 | L4
Enterprise AP Invoice Automation | [Software Coding] Enterprise Vendor Audit 2026 | ANALYTICS-E-271 | Invoice Analytics | Enterprise Excellence | Core | Large | Defining | L2 | Next | 2026-05-07 | 2026-09-22 | L4
Enterprise AP Invoice Automation | [Software Self-pay] Enterprise Vendor Audit 2027 | ANALYTICS-E-252 | Invoice Analytics | Enterprise Excellence | Core | Large | New | L1 | Later | 2027-01-06 | 2027-02-28 | L4
Enterprise AP Invoice Automation | [Software Telephony] Enterprise Vendor Audit 2027 | ANALYTICS-E-269 | Invoice Analytics | Enterprise Excellence | Core | Large | New | L1 | Later | 2027-11-10 | 2027-11-17 | L4
Enterprise AP Invoice Automation | [AP Automation] Enterprise Audit Data Automation & Results Delivery 2026 | ANALYTICS-E-258 | Invoice Analytics | Enterprise Excellence | Core | Large | Building | L4 | Now | 2025-12-18 | 2026-12-31 | L4
Enterprise AP Invoice Automation | [Coverage Discovery] Enterprise Vendor Audit 2026 Expansion | ANALYTICS-E-263 | Invoice Analytics | Enterprise Excellence | Core | Large | Defining | L2 | Now | 2025-12-18 | 2026-01-14 | L4
Finvi/ Artiva Optimization | Customer Service- FinVi /Artiva Optimize- Data Acquisition | DATA-E-381 | Data Platform | Platform | Platform |  | Building | L4 | Now | 2025-01-01 | 2026-02-25 | L4
Frictionless | [Frictionless¦MedNec/LOC Denials] Model Development and Implementation Feasibility | ANALYTICS-E-273 | Frictionless | Financial Clearance + Prediction | Innovation | Large | Defining | L2 | Next | 2026-04-01 | 2026-12-31 | L4
Frictionless | Frictionless - Clinical Denial Prevention Phase 1 (leveraging Clinical notes and LLM) | ANALYTICS-E-221 | Frictionless | Financial Clearance + Prediction | Innovation | Small | Shipped | L6 | Now | 2025-05-15 | 2025-11-01 | L4
Frictionless | Frictionless - Clinical Denial Prevention Phase 2 (leveraging Clinical notes and LLMs) | ANALYTICS-E-264 | Frictionless | Financial Clearance + Prediction | Innovation | Small | Shipped | L6 | Now | 2025-10-09 | 2025-12-31 | L4
Frictionless | (AI COE) Denial Prevention - Insurance Auth Denials - Predictive Model | ANALYTICS-E-195 | Frictionless | Financial Clearance + Prediction | Innovation |  | Shipped | L6 | Now | 2025-03-24 | 2025-12-17
Frictionless | Authorization Predictive Determination for Denial Prevention Automation (Frictionless) | FRONTRCM-E-187 | EIQ Clear | Financial Clearance + Prediction | Innovation |  | Shipped | L6 | Now | 2025-05-22 | 2025-12-17
Frictionless | Frictionless - Referral and Authorization expansion for denial avoidance | MDM-E-59 | EIQ Clear | Financial Clearance + Prediction | Innovation |  | Shipped | L6 | Now | 2025-06-16 | 2026-10-31
Frictionless | Frictionless- Support Product Innovation Auto Denial Avoidance / | DATA-E-385 | EIQ Clear | Financial Clearance + Prediction | Innovation |  | Shipped | L6 | Now | 2025-04-21 | 2025-10-08
Frictionless | Predictive CPT Enhancements | FRONTRCM-E-145 | EIQ Clear |  | Innovation | Large | Building | L4 | Now | 2025-10-09 | 2026-06-30
GenAI Clinical Appeals - Phase 2 | Store previously pulled clinical data in a central location accessible via EIQ vs. current shared file or DB today. | BACKRCM-E-878 | Clinical Appeals | Clinical | Strategic | Medium | New | L1 | Next | 2026-04-01 | 2026-09-30 | L4
GenAI Clinical Appeals - Phase 2 | GenAI - Create In-house EMRs for Non-Datavant Clients without Clinical Data using FHIR APIs | BACKRCM-E-737 | Clinical Appeals | Clinical | Strategic | Medium | Building | L4 | Now | 2025-10-23 | 2026-04-01 | L4
GenAI Clinical Appeals - Phase 2 | GenAI - Expanded denials - denied days, experimental, missed notification, no authoritization, and readmission | BACKRCM-E-794 | Clinical Appeals | Clinical | Strategic | Small | Building | L4 | Now | 2025-06-19 | 2026-05-15 | L4
GenAI Clinical Appeals - Phase 2 | GenAI - Expand to Clinical Appeal letters for All-Patient Refined (APR) DRGs | BACKRCM-E-735 | Clinical Appeals | Clinical | Strategic | Small | Shipped | L6 | Now | 2025-06-28 | 2025-10-08 | L4
GenAI Clinical Appeals - Phase 2 | GenAI - Expand to Payers - Traditional Medicaid/Medicare, MA for Length of Stay < 2 days & WC/Auto | BACKRCM-E-764 | Clinical Appeals | Clinical | Strategic | Small | Shipped | L6 | Now | 2025-05-22 | 2025-06-04 | L4
GenAI Clinical Appeals - Phase 2 | GenAI - Expansion Enabler - Provide Ops admins the configurability to enable or disable GenAI for clinical appeal reasons via EIQ UI | BACKRCM-E-767 | Clinical Appeals | Clinical | Strategic | Small | Shipped | L6 | Now | 2025-05-22 | 2025-07-30 | L4
GenAI Clinical Appeals - Phase 2 | GenAI - Expansion to Clients that do not provide Text Based/Indexed EMR PDFs | BACKRCM-E-707 | Clinical Appeals | Clinical | Strategic | Small | Shipped | L6 | Now | 2025-02-24 | 2025-12-17 | L4
GenAI Clinical Appeals - Phase 2 | GenAI - Modify clinical guideline subset & regenerate letters for enhanced review & reduction in time spent | BACKRCM-E-741 | Clinical Appeals | Clinical | Strategic | Medium | Building | L4 | Next | 2026-02-27 | 2026-09-30 | L4
GenAI Clinical Appeals - Phase 2 | GenAI - Rewrite Clinical GenAI Engine to improve quality, scalability and user experience | BACKRCM-E-840 | Clinical Appeals | Clinical | Strategic | Medium | Building | L4 | Now | 2025-07-31 | 2026-02-28 | L4
GenAI Clinical Appeals - Phase 2 | GenAI - Technical Appeal Packets using Clinical Data driven In-house Electronic Medical Records | BACKRCM-E-842 | Clinical Appeals | Clinical | Strategic | Small | Building | L4 | Now | 2025-12-18 | 2026-02-25 | L4
HL7 to Data Lake | Acute - HL7 ( Mercy) | DATA-E-227 | Data Platform | Platform | Platform |  | Shipped | L6 | Now | 2024-05-01 | 2025-05-31
HL7 to Data Lake | Acute - HL7 - Scaling all clients | DATA-E-266 | Data Platform | Platform | Platform |  | New | L1 | Now | 2025-05-01 | 2026-05-31
HL7 to Data Lake | HL7- P&A | DATA-E-214 | Data Platform | Platform | Platform |  | New | L1 | Now | 2024-05-06 | 2024-06-10
HL7 to Data Lake | Sup- HL7 ADT | DATA-E-179 | Data Platform | Platform | Platform |  | Shipped | L6 | Now | 2024-06-10 | 2024-07-15
HL7 to Data Lake | Sup- HL7 MDM | DATA-E-181 | Data Platform | Platform | Platform |  | New | L1 | Later | 2026-06-01 | 2026-10-31
HL7 to Data Lake | Sup- HL7 ORM- Pilot | DATA-E-180 | Data Platform | Platform | Platform |  | New | L1 | Later | 2026-06-01 | 2026-10-31
HL7 to Data Lake | Sup- HL7 ORU | DATA-E-183 | Data Platform | Platform | Platform |  | New | L1 | Later | 2026-06-01 | 2026-10-31
HL7 to Data Lake | Sup- HL7 SIU | DATA-E-182 | Data Platform | Platform | Platform |  | Shipped | L6 | Later | 2026-06-01 | 2026-10-31
Data acquisition | Industry Standard Data for Medicare / CMS / etc. | DATA-E-265 | Data Platform | Platform | Platform |  | New | L1 | Next | 2026-04-01 |  | L2
Initial Review Automation | Appeal Strength Calculator | BACKRCM-E-844 | EIQ Collect | Revenue Protection + Payer | Core |  | Shipped | L6 | Now | 2025-07-31 | 2025-10-21 | L3
Initial Review Automation | Appeal Audits When Upheld | BACKRCM-E-1009 | IR Automation | Financial Clearance + Prediction | Core | Medium | New | L1 | Later | 2026-07-01 | 2027-01-01 | L3
Initial Review Automation | EIQ Collect - Clinical Denial Appeals Analytics | BACKRCM-E-843 | IR Automation | Financial Clearance + Prediction | Core |  | Will not implement |  | Kill | 2026-04-02 | 2026-07-01 | L3
Initial Review Automation | Max Allowable Adjustment | BACKRCM-E-821 | EIQ Collect | Financial Clearance + Prediction | Core |  | Building | L4 | Now | 2025-07-31 | 2026-02-25 | L3
Initial Review Automation | Automate Creation of Appeal Record and Autopopulate | BACKRCM-E-839 | IR Automation | Revenue Protection + Payer | Core |  | Building | L4 | Now | 2025-06-18 | 2026-03-29 | L3
Initial Review Automation | Automate Next level provider appeal and show appeal history | BACKRCM-E-997 | IR Automation | Revenue Protection + Payer | Core |  | Building | L4 | Next | 2025-12-29 | 2026-05-30 | L3
Initial Review Automation | Document acquisition for appeal packets | BACKRCM-E-841 | IR Automation | Revenue Protection + Payer | Core |  | New | L1 | Next | 2026-04-01 | 2026-08-01 | L3
Initial Review Automation | Audit Compliance - Automate monthly client reports | BACKRCM-E-850 | IR Automation | Revenue Protection + Payer | Core | Medium | New | L1 | Later | 2026-09-06 | 2027-01-06 | L3
Initial Review Automation | Automate Confirmation Audit was Received | BACKRCM-E-849 | IR Automation | Revenue Protection + Payer | Core | Medium | New | L1 | Later | 2027-01-08 | 2027-03-31 | L3
Initial Review Automation | Retrieve audit request and create audit case | BACKRCM-E-847 | IR Automation | Revenue Protection + Payer | Core | Large | New | L1 | Later | 2026-06-30 | 2026-11-30 | L3
Insurance Verification Enhancements | Insurance Plan Selection Automation | FRONTRCM-E-159 | EIQ Clear | Financial Clearance + Prediction | Strategic | Large | Defining | L2 | Later | 2027-07-01 | 2028-03-30 | L3
Insurance Verification Enhancements | Integrated Waystar Self Pay Coverage Discovery | FRONTRCM-E-160 | EIQ Clear | Financial Clearance + Prediction | Strategic | Medium | Defining | L2 | Later | 2027-01-01 | 2027-06-30 | L3
Insurance Verification Enhancements | Post Insurance Benefit Note to Epic | FRONTRCM-E-161 | EIQ Clear | Financial Clearance + Prediction | Strategic | Small | Defining | L2 | Later | 2026-09-24 | 2026-11-18 | L3
Inventory Management | Billing Other Clearing House | MDM-E-60 | Data Platform | Platform | Strategic |  | Defining | L2 | Now | 2025-12-18 | 2026-03-31
Payer Enrollments & Access | Zelis workflow automation | BACKRCM-E-873 | Cash Automation | Revenue Protection + Payer | Strategic |  | New | L1 | Later | 2027-10-01 | 2028-03-31 | L2
Payer Enrollments & Access | Agent for payer portals to maintain ERA/EFT setups and 835 Enrollment | BACKRCM-E-872 | Cash Automation | Financial Clearance + Prediction | Strategic |  | New | L1 | Later | 2027-04-01 | 2027-09-30 | L2
Payer Enrollments & Access | Lockbox OCR enrollment automation agent | BACKRCM-E-874 | Cash Automation | Financial Clearance + Prediction | Strategic |  | New | L1 | Later | 2028-04-01 | 2028-09-30 | L2
Phreesia | Patient engagement for Non-Epic | INTER-E-245 | Data Integration | Patient Engagement | Strategic | Large | New | L1 | Next | 2026-04-06 | 2026-12-31
PreRegistration Worklist | Ensuite PreRegistration productivity dashboard | FRONTRCM-E-153 | EIQ Clear | Financial Clearance + Prediction | Strategic |  | Defining | L2 | Later | 2027-09-01 | 2027-11-30 | L3
PreRegistration Worklist | NSA/Self Pay PreRegistration Inventory Assignment Rules | FRONTRCM-E-154 | EIQ Clear | Financial Clearance + Prediction | Strategic | Medium | Defining | L2 | Next | 2026-05-07 | 2026-09-09 | L3
PreRegistration Worklist | Predictive analytics for PreRegistration estimate accuracy per CPT/payor | FRONTRCM-E-155 | EIQ Clear | Financial Clearance + Prediction | Strategic | Medium | Will not implement |  | Kill | 2026-10-01 | 2026-12-31 | L3
PreRegistration Worklist | Pre-registration Module | FRONTRCM-E-138 | EIQ Clear | Financial Clearance + Prediction | Strategic | Medium | Defining | L2 | Next | 2026-02-26 | 2027-01-27 | L3
PreRegistration Worklist | Red/Green Registration Light worklist | FRONTRCM-E-156 | EIQ Clear | Financial Clearance + Prediction | Strategic |  | Will not implement |  | Kill | 2026-10-01 | 2026-12-31 | L3
PreRegistration Worklist | Standardized PreRegistration Inventory Assignment Rules | FRONTRCM-E-157 | EIQ Clear | Financial Clearance + Prediction | Strategic | Medium | Defining | L2 | Later | 2026-09-24 | 2027-01-27 | L3
PreRegistration Worklist | Visual of PreRegistration estimate status (auto created vs auto finalized) | FRONTRCM-E-158 | EIQ Clear | Financial Clearance + Prediction | Strategic | Small | Defining | L2 | Next | 2026-05-07 | 2026-09-09 | L3
Provisioning | RPA - Client Provisioning | RPA-E-72 | Data Integration | Enterprise Excellence | Strategic | Medium | Building | L4 | Now | 2025-12-01 | 2026-03-31 | L4
Provisioning | Provisioning - Data acquisition - Workday data and Service Now data | MDM-E-65 | Data Platform | Enterprise Excellence | Strategic |  | Will not implement |  | Kill | 2025-07-31 | 2025-10-08 | L4
QA Automation (Reg QA) | QA Automation (Reg QA) | FRONTRCM-E-206 | EIQ Clear | Financial Clearance + Prediction | Strategic | Large | Defining | L2 | Later | 2027-05-03 | 2027-07-01
QA Automation (Reg QA) | Registration QA - Extended Quality Scoring (Future) | FRONTRCM-E-210 | EIQ Clear | Financial Clearance + Prediction | Strategic |  | Defining | L2 | Later | 2027-05-03 | 2027-09-15
QA Automation (Reg QA) | Registration QA - External Data Verification Sources (Future) | FRONTRCM-E-209 | EIQ Clear | Financial Clearance + Prediction | Strategic |  | Defining | L2 | Later | 2027-09-01 | 2027-10-31
QA Automation (Reg QA) | Registration QA - Interval Quality Scoring (MVP) | FRONTRCM-E-107 | EIQ Clear | Financial Clearance + Prediction | Strategic |  | Defining | L2 | Later | 2026-11-02 | 2027-01-31
QA Automation (Reg QA) | Registration QA - Pre Access Implementation (MVP) | FRONTRCM-E-211 | EIQ Clear | Financial Clearance + Prediction | Strategic |  | Defining | L2 | Later | 2026-12-16 | 2027-04-30
QA Automation (Reg QA) | Registration QA - RCM Platform Enabler (RPE) (MVP) | FRONTRCM-E-106 | EIQ Clear | Financial Clearance + Prediction | Strategic |  | Defining | L2 | Later | 2026-12-16 | 2027-04-30
QA Automation (Reg QA) | Registration QA - Workflow for Disputes and override (Future) | FRONTRCM-E-208 | EIQ Clear | Financial Clearance + Prediction | Strategic |  | Defining | L2 | Later | 2027-07-12 | 2027-09-15
Virtual Agent | Balance Inquiry - Balance Inquiry User Experience Improvements | BACKRCM-E-853 | Virtual Agent | Patient Engagement | Strategic |  | Building | L4 | Now | 2025-12-01 | 2026-01-15 | L4
Virtual Agent | Balance Inquiry - Improve Patient ID Success by Adding Prompts for Better Accuracy | BACKRCM-E-852 | Virtual Agent | Patient Engagement | Strategic |  | Building | L4 | Now | 2025-12-01 | 2025-12-31 | L4
Virtual Agent | Balance Inquiry - Provide Balance with Account Number as Input | BACKRCM-E-765 | Virtual Agent | Patient Engagement | Strategic | Medium | Shipped | L6 | Now | 2025-03-24 | 2025-09-30 | L4
Virtual Agent | Balance Inquiry - Provide balance with Date of Service as Input | BACKRCM-E-757 | Virtual Agent | Patient Engagement | Strategic | Medium | Shipped | L6 | Now | 2025-05-22 | 2025-10-08 | L4
Virtual Agent | Balance Inquiry - Provide Balance with Denial Information | BACKRCM-E-726 | Virtual Agent | Patient Engagement | Strategic | Medium | Building | L4 | Now | 2025-05-14 | 2025-11-30 | L4
Virtual Agent | Patient Access - Medicaid Eligibility Quick Screening - Virginia Only | BACKRCM-E-834 | Virtual Agent | Patient Engagement | Strategic | Large | New | L1 | Next | 2026-04-01 | 2026-12-31 | L4
VUR / UM Agent | Clinical summarization | UMPA-E-18 | VUR/UM Agent | Clinical | Strategic | Medium | Building | L4 | Now | 2025-07-01 | 2025-10-31 | L4
VUR / UM Agent | Improve clinical notes through denial reason insights | UMPA-E-25 | VUR/UM Agent | Clinical | Strategic | Medium | New | L1 | Now | 2025-12-01 | 2026-06-30 | L4
VUR / UM Agent | Present clinical notes for Physician Advisory P2P | UMPA-E-24 | VUR/UM Agent | Clinical | Strategic | Medium | New | L1 | Next | 2026-05-01 | 2026-11-30 | L4
VUR / UM Agent | Worklist mgmt and nurse assignment | UMPA-E-19 | VUR/UM Agent | Clinical | Strategic | Small | Building | L4 | Now | 2025-07-01 | 2025-12-31 | L4